## Project Classification
Consider the project factors in the list hand column of the table and determine the project risk. Enter the value in the right column and when all rows are completed, add all the values to arrive at the project risk total score to determine the project risk level.
Project Classification—Risk Matrix
Factors | Low (0) | Medium (1) | High (2) | Score
Project Team Size (number of staff members) | <5 | 5 – 9 | >9 |  | 0
Number of Teams Involved | 1 – 2 | 3 – 5 | >6 |  | 1
Complexity of Project (Multiple sub-projects) | Standalone system. | Some integration with another system. | New system needs to integrate with several others, and/or are critical systems. |  | 2
Project Duration | <3 months | 4 – 12 months | > 12 months
Technology/Business Process | Expert | Familiar | New to UIHC
Organizational Impact/Priority | Division Area | Spans Multiple departments | Hospital wide
Total Score |  |  |  | 0
Project Classification Calculation | Small/Low (0) | Medium (1) | Large/High (2) | Score
Work Effort | <80 hrs | 81 - 1000 hrs | >1000 hrs
Project Cost | <25K | 26-99K | >100K
Risk Level | 0 - 3 | 4 - 8 | 9 -12 | 0
Total Score |  |  |  | 0
| Based on the information you've entered: | This work effort is classified as a Small Project
Project Class | Small | Medium | Large
| 0 -1 | 2 -4 | 5 -6

## Project Deliverables by Class
Phase | Activities/Deliverables | Template | Project Class
|  |  | Small | Medium | Large | I am under construction.
Initiating
Initiating | Project Request Document (PID) | .doc | X | X | X | Please be patient with me.
| Business Case |  | X | X | X | Thanks, HCIS PMO
| Project Governance |  |  | X | X
| Project Classification & Sizing | .xls | X | X | X
| Assign Project Manager/Lead |  |  | X | X
| Phase Sign-off/Closure Document | .doc |  | X | X
Planning
Planning | Planning Kick-Off Meeting |  |  | X | X
| Project Charter | .doc |  | X | X
| Project Approach |  | X | X | X
| Work Plan - Schedule Development | .doc |  | X | X
| Project Team Structure/Roles & Responsibilites | .doc |  | X | X
| Risk Management Plan |  |  |  | X
| Time Management Plan |  |  |  | X
| Cost Management Plan |  |  | X | X
| Resource Plan/Team assignments |  |  |  | X
| Issue Management Plan |  |  |  | X
| Communications Management Plan |  | X | X | X
| Scope Management Plan |  |  |  | X
| Phase Sign-off Document | .doc |  |  | X
Executing/Implementing
Executing Implementing | Project Kick -off Meeting |  |  | X | X
| Deliverables |  |  | X | X
| Manage Communications |  | X | X | X
| Manage Risks |  |  | X | X
| Manage Schedule |  |  | X | X
| Manage Scope |  | X | X | X
| Manage Costs |  |  | X | X
| Manage Issues |  |  | X | X
| Phase Sign-off/Closure Document | .doc |  |  | X
Closure
Closure | Formal Acceptance |  |  | X | X
| Transition to Production/Operations |  | X | X | X
| Contract Closure |  |  | X | X
| Lessons Learned |  |  |  | X
| Administrative Closure Documentation |  | X | X | X
| Project Sign-off/Closure Document | .doc | X | X | X
| Celebrate |  |  | X | X
Monitoring & Controlling
Monitoring & Controlling | Status Report | .doc | X | X | X
| Visual Project Plan | .xls |  | X | X
| Approved Changes |  |  | X | X
| Perfomance measures |  |  |  | X
| Contract changes |  |  |  | X
| Document Issues |  |  | X | X
| Conduct Status Review meetings |  |  | X | X
| Corrective actions |  |  |  | X
| Monitoring and Controlling Checklist |  |  |  | X
| Change Requests | .doc |  | X | X
Note on B5: Curtis Chung: This phase defines and organizes the project. The project justification is outlined in this phase
Note on B12: Curtis Chung: In this phase a workable project plan is developed that will accomplish the project goals & objectives.
Note on B36: Curtis Chung: This phase formalizes the acceptance of the project or product with the customer and documents lessons learned.
Note on C23: Curtis Chung: -Collect Requirements -Define Scope -Create Work Breakdown Strurcture
Note on C18: Curtis Chung: -Define Activities -Sequence Activities -Estimate Activity Resources -Estimate Activity Duration -Develop Schedule
Note on C7: Curtis Chung: -Identify Sponsors
Note on C19: Curtis Chung: -Estimate Costs -Determine Budget & Budget process
Note on C17: Curtis Chung: -Plan Risk Management -Identify Risks -Perform Qualitative Analysis -Plan Risk Responses